Warsaw, 28th July 2011

Timetable for GPC to provide contribution on ERA (Summer & Autumn 2011)

mid July	formation of the GPC Task Force

25th July	initial contribution by the TF members

28th July	1st TF meeting – to discuss the content and distribution of work

8th Aug	comments by the TF members on the proposed structure of the GPC contribution; decision on work distribution

25th Aug	contribution by the TF members to a 1st draft of the GPC contribution

31st Aug	the 1st draft distributed for comments to TF

2nd Sep	deadline for response by the TF members

5th Sep	the 1st draft sent to GPC

7th Sep	GPC plenary meeting (half day) – discussion of the 1st draft

16th Sep	the 2nd draft distributed for comments to TF; consulting the 2nd draft with JPIs coordinators

20th Sep	deadline for response by the TF members and JPIs coordinators

23rd Sep	concluding the final draft within TF

26th Sep	the final draft sent to the ERAC Vice Chair and to GPC

3rd Oct	deadline for response by the GPC delegates

7th Oct	finalising the GPC’s contribution to ERAC on the ERA Framework

10th Oct	GPC plenary meeting (full day) - discussion and approval of the GPC’s contribution, delivery to ERAC